## Slide 1
Kevin Mann
October, 2017
Project Management at Plantronics
With an Industry Case Study on Risk Management

## Slide 2
Plantronics Overview
Project Management Overview
Project Management Office at Plantronics
Project Roles & Responsibilities
Risk Management & Case Study

## Slide 3: Company Overview
Leader in contact center, consumer Bluetooth® and business communications devices
Strong financial position
  Over $850 million in annual revenues (USD)
  Positive cash flow for more than 20 years
Headquarters in Santa Cruz, California
  Offices in more than 30 countries, with major hubs in the Netherlands, China, UK, and Mexico
  More than 3,000 employees worldwide

## Slide 4: Growth through innovation
$M
Chart: 
| 1964 | 1979 | 1980 | 1981 | 1982 | 1983 | 1984 | 1985 | 1986 | 1987 | 1988 | 1989 | 1990 | 1991 | 1992 | 1993 | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013
Audio Communications Group | 0.8507 | 37.9 | 40.6 | 43.3 | 46 | 41.2 | 48.1 | 48.2 | 55.7 | 69.4 | 78.1 | 84.4 | 90.7 | 94.5 | 95.8 | 112.267 | 133.966 | 169.923 | 182.959 | 195.3 | 236.1 | 282.546 | 309.143 | 390.748 | 311.181 | 337.508 | 417 | 560 | 629.7 | 676.5 | 747.9 | 674.6 | 613.8 | 683.6 | 713.4 | 762.2
1981
1984
1987
1990
1993
1996
1999
2002
2005
2008
2011
1964
2012
2013
Voyager
Legend
BBGO
CS70
SupraPlus
Supra
M10
Duoset
Encore
DA60
Voyager
510s
CS50
Savi 700
Office Corded
Wireless
UC
Contact Center
Aviation & TelCo
of yearly revenue
invested as R&D
8-10%

## Slide 5: Unified Communications
One of many definitions:
Communications being integrated in order to optimize business processes.
This means that an organization is able to seamlessly integrate, or unify, its typical business processes with both real-time communications (such as instant messaging/chat, presence information, telephony/VoIP and video conferencing) and non real-time communications (such as integrated voicemail, e-mail, SMS and fax).

## Slide 6
1960
2015
2009
Savi 700 unifies PC and desk phone
communications
2012
Plantronics Mexico
celebrates 40 years
in Tijuana
2003
CS50 brings wireless freedom to the office
2000
Digitally enhanced USB headsets for the PC and Mac are introduced
1995
FreeHand, an ultra-lightweight in-the-ear headset, is introduced
1983
The new StarSet Supra soon becomes the call center industry standard
1969
First words from the moon spoken through a Plantronics headset
1961
Pacific Plantronics is incorporated
1963
FAA selects Plantronics
as sole headset provider
2013
Contextual intelligence expanded in Voyager and Blackwire Families
2014
Voyager Edge blends contextual intelligence and minimalist design
2011
Contextual intelligence introduced with Voyager PRO UC
2015
Voyager Focus UC brings together UC, context, wireless, and Active Noise Cancellation
Notes: Add device for 2016 for Q2 FY17

## Slide 7: Product Portfolio
Mobile Stereo
Enterprise & Unified Communications
Voyager Edge UC
Savi Family
BackBeat SENSE
Gaming
BackBeat FIT
RIG 500 Series
RIG 4VR

## Slide 8: Software and Services
PLANTRONICS HUB
Plantronics Hub for desktop (Windows/Mac) and for mobile (Android/iOS)
Plantronics Manager Pro
Find MyHeadset
Plantronics Device as a Service (DaaS)
Notes: Plantronics Manager Pro is a cloud-based software that enterprise IT managers use to configure and update large-scale audio device implementations.
Plantronics DaaS is a subscription program for headsets and services.
Plantronics Hub is a client application used to configure device settings.
You can guess what Find My Headset is for.
Not shown is the Plantronics software development kit used to integrate apps with Plantronics devices to make the apps “contextually aware”.

## Slide 9
Project Management Overview

## Slide 10: What is a Project?
Projects are often confused with simply doing “business as usual.” However, projects have unique characteristics:
  A project is something that starts and ends; it is temporary
  A project may have similar elements to the core business, but is otherwise done for a unique purpose or goal
  A project involves unfamiliarity – something new or a significant change
Notes: Ask for input

## Slide 11: What is Not a Project?
A task list that you do repeatedly. Example: Generating a weekly report is not a project
Work that is done as part of general roles and responsibilities. Example: Running corporate training program is not a project
Anything that has a schedule or end date
Something that needs administrative oversight
Project Manager

## Slide 12: What is Project Management?
Project management is the application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.

## Slide 13: Project Management Triangle
Scope
Cost
Time
Notes: Project management is the task of balancing these 3 constraints.

## Slide 14: Pick Any Two
Good
Cheap
Fast
Slow
Expensive
Low Quality
Impossible
Notes: This triangle reflects the fact that the three properties of a project are interrelated, and it is not possible to optimize all three – one will always suffer

## Slide 15: Project Methodologies
Constraints: Scope Cost Time
Estimates: Cost Time Scope
Waterfall Project Agile Project
Notes: In a Waterfall project, the features (or scope) are first defined in detail, which drive cost and schedule estimates.
In an Agile project, cost and schedule are defined first, and scope depends on the team’s prioritization of the features.

## Slide 16: What is a Program?
A Program is a group of related projects that can be managed in a coordinated way to obtain benefits and control not available from managing them individually.

## Slide 17
Project Management Office at Plantronics

## Slide 18: What is a Project Management Office?
A Project Management Office (PMO) is a centralized group that defines and maintains standards for project management, program management, and portfolio management within the organization.

## Slide 19: What is Portfolio Management?
Is the centralized management of the processes, methods, and technologies used to analyze and collectively manage current or proposed projects based on numerous key characteristics.

## Slide 20: Project Portfolio Management (PPM)
“Doing the Right Things” is the basis for Portfolio Management
“Doing Things Right” is the basis for Project Management
Successful organizations invest in improving both disciplines
Doing the Right Things
Doing Things Right
Doing the Right Things Right
Portfolio Management
Project Management
Project Portfolio Management
Notes: Things: Initiatives, Projects and Programs

## Slide 21
PMO
Portfolio Management
Program Management
Project Management
Deliver Organizational Value
Strategy
Support / Guidance
Standards & Template
Governance
Deliver Business Value
Business Goal Alignment
Project Intake and Selection
Portfolio Optimization
Deliver Stakeholder Value
Multiple Projects
Align Projects to Program Benefit
Deliver Quality Products or Services
Scope, Cost, Schedule
Notes: PMO is an operational unit
PM is an action or something you do

## Slide 22: Goals of PMO & PPM at Plantronics
Ensure a common process for initiating and selecting projects
Define projects in a consistent and common manner
Ensure that projects align with goals (enterprise, department)
Provide a framework to facilitate decisions
Make better use of limited resources (people, funds)
Enable action for low value projects
Provide a comprehensive view of projects across the enterprise
Alignment
Transparency
Structured Intake

## Slide 23
Project Roles and Responsibilities

## Slide 24: Key Project Roles
Project Sponsor
Business Lead
Project Manager

## Slide 25
Project Sponsor
Business Lead
Project Manager
Responsible to the organization for delivery
Responsible for day to day delivery of the project
Responsible to the Sponsor delivering stated objectives

## Slide 26: Group Discussion: Roles and Responsibilities
What are the Top 5 responsibilities of
  Project Sponsor
  Business Lead
  Project Manager

## Slide 27: Project Sponsor
Responsible for benefits realization
Identifies, assigns Business Lead and critical project team members
Authorizes the scope of the project
Approves project documents
Approves business readiness
Helps to find solutions for escalated risks and issues
Helps drive change management
Authorizes project changes (scope, schedule, or cost)

## Slide 28: Business Lead
Shapes and owns the solution to the problem or opportunity
Responsible for defining solution requirements
Identifies and analyzes stakeholders, business impact and business readiness
Responsible for identifying risks and issues; escalating when needed
Responsible for Change Management and success of change
Secures the right business resources for participation; escalating as needed
Responsible for communications pertaining to solution or project results
Can answer questions or track down the answers/SMEs
Has day to day involvement in the project, in close partnership with the PM

## Slide 29: Project Manager
Produces and manages the project schedule and project budget
Captures and manages risk
Records issues and ensures issues are resolved
Ensures tasks are completed
Works to keeps project within agreed time, cost and scope
Creates and executes project communication plan
Ensure the project adheres to PMO guidelines
Escalates to business lead and sponsor as needed
Generally not a SME in the business or system
Notes: Schedule meetings and take notes! 

## Slide 30
Risk Management

## Slide 31: Definitions
Risk
  A future event that has a probability of occurring, and will have an impact on the project if it does.
Issue
  An event occurring in the present that is having an impact on the project, or may have an impact in the future.
Risk Management
  The processes for identifying, analyzing and responding to risks.
  Not performed one time; it is continuous throughout the life of the project

## Slide 32: Components of Risks
Event
Probability
Impact
Trigger
Response
Notes:   It is the risk event that Risk Management seeks to control first and foremost by finding ways to control the probability of the occurrence and then the impact if it does occur.

## Slide 33: Risk Management Processes and Sub-Processes
Risk Identification
  Research
  Investigation
Risk Quantification
  Prioritize Risks
Risk Response
  Avoidance
  Mitigation
  Acceptance
Risk Control
  Monitor for Risk Triggers
  Report
  Resolve

## Slide 34: Risk Identification
Identify project risks
Possible sources include:
  Historical Data
  Documentation Review
  SWOT Analysis
  Personal/Previous Experience
  Industry Studies/Standards
  Subject Matter Experts (internal or external)
  Team Members

## Slide 35: Risk Quantification
Establish a way of arranging risks in order of importance
Risk Severity: A product of the risk probability and impact
Probability | Impact | Severity
1 | 1 | 1
1 | 2 | 2
1 | 3 | 3
2 | 2 | 4
2 | 3 | 6
3 | 3 | 9
Low
Medium
High

## Slide 36: Risk Quantification
Can a Risk have 0% probability of occurring?
Can a Risk have 100% probability of occurring?

## Slide 37: Risk Response
Risk Response involves creating strategies that can be used to deal with risk. There are three main strategies:
Avoidance
Mitigation
Acceptance
Notes: Reference Page 174

## Slide 38: Response 1: Risk Avoidance
If at all possible any event that causes risk should be avoided. It is much easier and cost effective to avoid a risk than to manage one.
Must be implemented before the risk has materialized
Eliminates the root-causes of the risk
The probability of the event becomes zero
Notes: A team member will be on-call for jury duty. Replace that team member or reschedule their involvement.

## Slide 39: Response 2: Risk Mitigation
Mitigation strategies are activities performed prior to the materialization of the risk.
Three types of mitigation strategies:
Reduce Probability
Reduce Impact
Risk Deflection/Transfer
Notes: Deflection or Transfer is formally shifting ownership of the risk to another party. For example, an insurance agency to cover risk of fire.

## Slide 40: Response 3: Risk Acceptance
An acceptance strategy involves allowing the risk to materialize and having enough resources and time to properly absorb the effects of the risk and still deliver the project successfully.
Passive acceptance is letting the risk occur and accepting the impact.
Active acceptance is letting the risk occur but having a ‘Contingency Plan’ in place with funds, resources and activities preplanned.

## Slide 41: Contingency Plan
Step 1
Step 2
Step 3
Step 4
Goal
Plan
Event
Contingency Plan
Step 3a
Step 3b
Step 3c
Notes: If you make it to Step 3, and the event occurs, you are now dealing with an active issue, and you have missed the opportunity to incorporate risk contingency.

## Slide 42: Risk Management Example
Scenario: A key step in a software deployment is end user training
Risk Event: Training Room in unsatisfactory condition due to ongoing construction in the building
Impacted Activity:
End user training not completed on schedule
Avoidance:
Conduct training at another site
Deflection:
Software provider must be responsible for providing a satisfactory facility
Mitigation (Reduced Probability or Impact):
Review the construction schedule and plan training dates accordingly to minimize chance of conflict
Schedule rooms as far from the construction area as possible
Trigger:
Setup tour of the facility prior to training to assess condition
Obtain a point of contact to keep informed
Contingency: Conduct Web-Based Training

## Slide 43: Risk Control
Monitor and Manage Risks:
Document risks in a register
Assign owners to monitor for risk triggers
Provide regular risk updates to project stakeholders
Keep a record of risks handled, a description of corrective actions and costs involved
Escalate risks if they require additional support to resolve

## Slide 44
Case Study

## Slide 45: Case Study
One Program, Three Projects:
Project
Scope
1. Pricing Component of ERP
Upgrade
•
Build direct
data integration from
Enterprise Pricing
application to
ERP v2.0
•
Re
-
export all active prices (approx. 200k) to
ERP v2.0
to
support cut
-
over from
ERP v1.0
2. Multi
-
Currency Enablement
•
Replace obsolete, home
-
grown
Customer Pricing Portal
with
a new,
multi
-
currency enabled solution
•
Enhance
Enterprise Pricing
application with multi
-
currency
capability
3. Integrate Acquired
Company
•
Enhance
Enterprise Pricing
application to support new retail
use cases
•
Extract
& transform pricing data from acquired company’s
ERP and load into
Enterprise Pricing
application to support
cut
-
over

## Slide 46: Case Study
Multi-Currency
Enhancements for Acquisition
Data Conversion for Acquisition
Current-State:
Future-State:
Enterprise Pricing
Sales Data Mart
ERP
v1.0
ERP
v2.0
Enterprise Pricing
ERP customization exists here
Customer Pricing Portal
Customer Pricing Portal
Customization moved here

## Slide 47: Risks Register
Risk
Impact
Mitigation
1.
ERP
v2.0
upgrade is delayed
New
Customer Pricing Portal
cannot go
-
live
Reduce
Impact
2.
Enterprise Pricing
application enhancements
not completed on schedule
ERP
v2.0
cannot
go live
Reduce Probability
3. Acquired
company’s process are changing and
not yet finalized
Enterprise Pricing
app feature enhancements
are developed but
never used, or key
requirements are missed
Reduce Probability
4.
ERP
v2.0
go
-
live fails
Business stops
Contingency Plan

## Slide 48: Risk 1 Mitigation: Reduce Impact
Reduce the impact to Pricing systems in case the ERP v2.0 upgrade is delayed
Design the data interface to provide flexibility for ERP cut-over timing

## Slide 49: Risk Mitigation via Solution Design
Customer Pricing Portal and Enterprise Pricing changes go-live on their own schedule
ERP v2.0 cut-over is a pull from a data staging table
Sales Data Mart
ERP v1.0
ERP v2.0
Enterprise Pricing
Staging Table
Push
Customer Pricing Portal
Pull

## Slide 50: Risk 2 Mitigation: Reduce Probability
Reduce the probability of Enterprise Pricing app enhancements not being completed on schedule
Measure development team’s rate of completing work
Extrapolate time required to complete remaining work

## Slide 51: Risk Trigger
Remaining work does not project to zero by project completion date
Risk: Required work will not be completed by scheduled end date
Mitigation: Reduce probability by adding a development resource
Chart: Burndown
Baseline | 100 | 94.45 | 88.9 | 83.35 | 77.8 | 72.25 | 66.7 | 61.15 | 55.6 | 50.05 | 44.5 | 38.95 | 33.4 | 27.85 | 22.3 | 16.75 | 11.2 | 5.65
Remaining | 100 | 91 | 90 | 88 | 83 | 79 | 75 | 68 | 66 | 64 | 61
Projected | 61 | 57.5 | 54 | 50.5 | 47 | 43.5 | 40 | 36.5

## Slide 52: Risk Control
Chart: Burndown
Baseline | 100 | 94.45 | 88.9 | 83.35 | 77.8 | 72.25 | 66.7 | 61.15 | 55.6 | 50.05 | 44.5 | 38.95 | 33.4 | 27.85 | 22.3 | 16.75 | 11.2 | 5.65
Remaining | 100 | 91 | 90 | 88 | 83 | 79 | 75 | 68 | 66 | 64 | 61 | 58 | 53 | 46 | 37 | 27 | 13 | 5
Additional development resource is added
Track effectiveness of mitigation
Monitor until probably or risk approaches zero

## Slide 53: Risk 3 Mitigation: Reduce Probability
Reduce the probability of developing unused features or missed requirements due to evolving business processes

## Slide 54: Risk Mitigation via Project Methodology
With Agile, risk of missed requirements decreases over time:
  Incremental delivery of new features allows business feedback earlier
  Continuous reprioritization of the feature backlog over the course of the project
Chart: Agile Project
Value Delivery | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Risk | 5 | 4.1 | 3.3 | 2.6 | 2 | 1.5 | 1.1 | 0.8 | 0.6 | 0.5
Chart: Waterfall Project
Value Delivery | 10
Risk | 5 | 5.2 | 5.5 | 5.9 | 6.4 | 7 | 7.7 | 8.5 | 9.4 | 10.4
Notes: Risk = Missed Requirements and Unused Features

## Slide 55: Risk 4 Mitigation: Contingency Plan
Ensure business continuity in case the ERP 2.0 go-live fails
Design the data interfaces such that pricing data remains in-sync between ERP 1.0 and 2.0 in case a roll-back is required
Sales Data Mart
ERP 1.0
ERP 2.0
Enterprise Pricing
Staging Table
Automated Variance Report

## Slide 56
Plantronics Overview
Project Management Overview
Project Management Office at Plantronics
Project Roles & Responsibilities
Risk Management & Case Study
Summary

## Slide 58: Risks
Risk | Impact | Mitigation
1. ERP v2.0 upgrade is delayed | New Customer Pricing Portal cannot go-live | Reduce Impact
2. Enterprise Pricing application enhancements not completed on schedule | ERP v2.0 cannot go live | Reduce Probability
3. Acquired company’s process are changing and not yet finalized | Enterprise Pricing system feature enhancements are developed but never used, or key requirements are missed | Reduce Probability
4. ERP v2.0 go-live fails | Business stops | Contingency Plan

## Slide 59: Case Study
One Program, Three Projects:
Project | Scope
1. Pricing Component of ERP Upgrade | Build direct data integration from Enterprise Pricing application to ERP v2.0 Re-export all active prices (approx. 200k) to ERP v2.0 to support cut-over from ERP v1.0
2. Multi-Currency Enablement | Replace obsolete, home-grown Customer Pricing Portal with a new, multi-currency enabled solution Enhance Enterprise Pricing application with multi-currency capability
3. Integrate Acquired Company | Enhance Enterprise Pricing application to support new retail use cases Extract & transform pricing data from acquired company’s ERP and load into Enterprise Pricing application to support cut-over